## Sheet1
Test ID | Feature/Function | Test Input | Expected Output | Actual Output | Objective | Test Type | Result
TC001 | Account Creation | Valid email and password | Account created successfully | Account created successfully | Verify new user can create an account | UAT | Pass
TC002 | Login | Valid email and password | User logged in successfully | User logged in successfully | Verify existing user can log in | System | Pass
TC003 | Browse Products | Category: Electronics | Display products in Electronics category | Products not loading | Verify products can be browsed by category | Integration | Fail
TC004 | Add to Cart | Product ID: P101 | Product P101 added to cart | Product P101 added to cart | Verify product can be added to cart | Unit | Pass
TC005 | View Cart | Cart contains Product P101 Ã—1 | Display all items in cart with correct quantities and prices | Cart showing wrong quantity | Verify cart contents are displayed correctly | System | Fail
TC006 | Checkout | Credit Card details | Order placed successfully and confirmation email sent | Order placed successfully | Verify checkout process with credit card | UAT | Pass
TC007 | Order Confirmation | Successful purchase | Confirmation email received within 1 minute | Confirmation email received | Verify order confirmation email delivery | Integration | Pass
TC008 | Admin Product Management | Add new product details | New product added to catalog | New product added | Verify admin can add new products | System | Pass
TC009 | Admin Sales Reports | Date range: Last Month | Sales report for last month displayed | Sales report displayed | Verify admin can view sales reports | UAT | Pass
TC010 | Order Tracking | Valid Order ID | Order status and estimated arrival displayed | Order status displayed | Verify customer can track order status | System | Pass
TC011 | Account Creation | Invalid email format | Error message: Invalid email format | Error message: Invalid email format | Verify account creation fails with invalid email | Unit | Pass
TC012 | Login | Invalid password | Error message: Invalid credentials | Error message: Invalid credentials | Verify login fails with incorrect password | Unit | Pass